## Sheet1
Product Backlog
Product Backlog Item | Prioritization | Estimate (Size) | Sprint | Status
Allocate scrum team roles | Medium | Mouse | 1
Create shared github repository | Medium | Mouse | 1
Data collection from organisation | High | Dog | 1
Confirm who will need to access the system and determine what privileges they require | Medium | Mouse | 1
Insert SQL database supplied by organisation | High | Dog | 2
System must report on countries population in the world basis | High | Deer
System must report on countries population in a continent basis | High | Deer
System must report on countries population in a regional basis | High | Deer
Ability to organise by largest to smallest/smallest to largest population - This is required for world, continents, regions, countries, districts, capital cities | High | Deer
System must report on cities population in the world basis | High | Deer
System must report on cities population in a continent basis | High | Deer
System must report on cities population in a regional basis | High | Deer
System must report on cities population in a country basis | High | Deer
Allow users to run System must reports on manually entered number of populations | High | Deer
System must report can identify capital cities within listed cities | High | Deer
System must report on capital cities population in the world basis | High | Deer
System must report on capital cities population in a continent basis | High | Deer
System must report on capital cities population in a regional basis | High | Deer
System must report on population living in cities within a continent | High | Hippo
System must report on population living out with cities within a continent | High | Hippo
System must report on population living in cities within a region | High | Hippo
System must report on population living out with cities within a region | High | Hippo
System must report on population living in cities within a country | High | Hippo
System must report on population living out with cities within a country | High | Hippo
System must reports on population of the world | High | Deer
System must reports on population of a continent | High | Deer
System must reports on population of a region | High | Deer
System must reports on population of a country | High | Deer
System must reports on population of a district | High | Deer
System must reports on population of a city | High | Deer
Organisation would like the ability to run a report on number of people who speak specified languages from greatest to smallest, including their percentage in the world | High | Elephant
Link two tables within SQL database - countrylanguage & population | High | Deer
Sort by population - Ascending | High | Mouse
Create view to include the following columns; Language, country code, population and percentage | High | Dog
Create view for all country table based reports to include the following columms: Code, Name, Continent, Region & Population | High | Dog
Create view for all city table based reports to include the following columms: Name, Country, District & Population | High | Dog
Create view for all capital city based reports to include the following columms: Name, Country & Population | High | Dog
Create view for population reports to include the following columns: Name, total population, total population in cities (% format) and total population not living in cities (% format) | High | Deer
Identify population for people living within cities for each country | High | Deer
Identify population for people living out with cities for each country | High | Deer
Create GUI to allow users to enter number(N) of population | Medium | Deer
Update organisation on progress | Low | Mouse